## mydoctor-app-developm
MyDoctor App development
Agile Project Management for HTC Group 1. NU Data Science Spring 2021
Business Understanding - Week 1-2
Name | Owner | Status | Priority | Type | Deadline | Time Est. | Time Spent | Gap | Timeline - Start | Timeline - End | Dependent On
Understand remote diagnosis | Parviz Ali | Need Info | High | MILESTONE! | 2021-06-04 | 40 | 20 | 20 | 2021-05-28 | 2021-06-04
Common symptoms and diseases | Sean Yuan | Need Info | High | MILESTONE! | 2021-06-05 | 40 | 20 | 20 | 2021-05-28 | 2021-06-11
Insurance provider networks | Ben Prescott | Need Info | Medium | MILESTONE! | 2021-06-05 | 20 | 20 | 0 | 2021-05-31 | 2021-06-08
[5 empty] | 2021-06-04 to 2021-06-05 | 100 | 60 | 40 | 2021-05-28 | 2021-06-11
Data Understanding - Week 3-4
Name | Owner | Status | Priority | Type | Deadline | Time Est. | Time Spent | Gap | Timeline - Start | Timeline - End | Dependent On
Patient audio (input audio) into Google’s NLP AI | Parviz Ali, Sean Yuan | Open | Must Have | Increment | 2021-06-06 | 80 | 0 | 80 | 2021-06-03 | 2021-06-19 | Common symptoms and diseases, Understand remote diagnosis, Which diseases can be diagnosed remotely?
Text Dialogue + ICD 10 data | Kasia Kostyuk | Open | Must Have | Increment | 2021-06-13 | 80 | 0 | 80 | 2021-06-04 | 2021-06-19 | Understand remote diagnosis, Which diseases can be diagnosed remotely?
Combining medical data and patient’s data | Ben Prescott | Open | High | Increment | 2021-06-09 | 80 | 0 | 80 | 2021-06-02 | 2021-06-16 | Common symptoms and diseases, Insurance provider networks
[5 empty] | 2021-06-06 to 2021-06-13 | 240 | 0 | 240 | 2021-06-02 | 2021-06-19
Data Preparation - Week 5-6
Name | Owner | Status | Priority | Type | Deadline | Time Est. | Time Spent | Gap | Timeline - Start | Timeline - End | Dependent On
Audio, NLP data | Ben Prescott, Kasia Kostyuk | Needs Product | High | Increment | 2021-06-12 | 10 |  | 10 | 2021-06-11 | 2021-06-25 | Patient audio (input audio) into Google’s NLP AI
Symptoms and ICD10 data | Parviz Ali, Sean Yuan | Needs Product | High | Increment | 2021-06-10 | 12 |  | 12 | 2021-06-02 | 2021-06-11 | Text Dialogue + ICD 10 data
[5 empty] | 2021-06-10 to 2021-06-12 | 22 | 0 | 22 | 2021-06-02 | 2021-06-25
Modeling - Week 7-8
Name | Owner | Status | Priority | Type | Deadline | Time Est. | Time Spent | Gap | Timeline - Start | Timeline - End | Dependent On
Speech to text | Parviz Ali | Not Started | High | Increment | 2021-06-30 | 5 |  | 5 | 2021-05-12 | 2021-05-26 | Understand remote diagnosis, Audio, NLP data
Classification of symptoms | Sean Yuan | Not Started | Medium | Increment | 2021-06-30 | 17 |  | 17 | 2021-06-10 | 2021-06-24 | Common symptoms and diseases, Combining medical data and patient’s data
Unstructured input data capture | Kasia Kostyuk | Not Started | High | Increment | 2021-06-30 | 8 |  | 8 | 2021-06-10 | 2021-06-24 | Patient audio (input audio) into Google’s NLP AI, Common symptoms and diseases, Understand remote diagnosis, Visual and other data
Predict questions + classify symptoms | Kasia Kostyuk, Ben Prescott | Not Started | Must Have | Bug | 2021-06-30 | 12 |  | 12 | 2021-06-10 | 2021-06-24 | Video data, Audio, NLP data, Gather and organize library of medical symptoms
[5 empty] | 2021-06-30 | 42 | 0 | 42 | 2021-05-12 | 2021-06-24
Evaluation - Week 9-10
Name | Owner | Status | Priority | Type | Deadline | Time Est. | Time Spent | Gap | Timeline - Start | Timeline - End | Dependent On
Remote patient cases resolved % | Parviz Ali | Not Started | Medium | Increment | 2021-07-18 | 14 |  | 14 | 2021-04-24 | 2021-05-01 | Patient audio (input audio) into Google’s NLP AI, Unstructured input data capture, Video data, Common symptoms and diseases, Understand remote diagnosis, Which diseases can be diagnosed remotely?, NLP Data to text, Audio, NLP data, Speech to text, Pilot with a clinic, Visual and other data
Total patient vs remote a doctor visit | Sean Yuan | Not Started | Low | Increment | 2021-07-18 | 12 |  | 12 | 2021-05-23 | 2021-05-30 | Pilot with a clinic
Patient satisfaction survey | Sean Yuan | General | General | General | 2021-07-18 | 20 |  | 20 | 2021-06-21 | 2021-06-28 | Patient satisfaction data
Average time and dollar saved by patient and clinic | Kasia Kostyuk | General | General | General | 2021-07-18 | 20 |  | 20 | 2021-04-24 | 2021-05-01 | Remote patient cases resolved %, Pilot with a clinic
[5 empty] | 2021-07-18 | 66 | 0 | 66 | 2021-04-24 | 2021-06-28
Deployment - Week 11-12
Name | Owner | Status | Priority | Type | Deadline | Time Est. | Time Spent | Gap | Timeline - Start | Timeline - End | Dependent On
Pilot with a clinic | Kasia Kostyuk | Not Started | Medium | Increment | 2021-08-29 | 40 |  | 40 | 2021-06-09 | 2021-07-15 | Classification of symptoms, Unstructured input data capture, Predict questions + classify symptoms, Combining medical data and patient’s data, Speech to text, Gather and organize library of medical symptoms, Insurance provider networks
A/B testing. Doctors with AI access vs no AI access | Sean Yuan | Not Started | Low | Increment | 2021-08-29 | 40 |  | 40 | 2021-04-21 | 2021-05-20 | Classification of symptoms, Unstructured input data capture, Predict questions + classify symptoms, Speech to text, Pilot with a clinic
Expand to other clinics | Parviz Ali | General | General | General | 2021-09-26 | 40 |  | 40 | 2021-06-08 | 2021-07-21 | Pilot with a clinic, A/B testing. Doctors with AI access vs no AI access
Improve models | Parviz Ali | General | General | General | 2021-09-26 | 10 |  | 10 | 2021-04-18 | 2021-05-29 | Remote patient cases resolved %, Total patient vs remote a doctor visit, Patient satisfaction survey, Average time and dollar saved by patient and clinic
[5 empty] | 2021-08-29 to 2021-09-26 | 130 | 0 | 130 | 2021-04-18 | 2021-07-21