## Sheet1
Name | Activities | Predecessor | Normal Time (days) | Crash Time (days) | Normal Cost | Crash Cost | Activity Time Difference (Normal - Crash) | Added Cost for Crashing | Crash cost/time | Days to be crashed
LTEs
Develop Infrastructure as Code Templates | A |  | 5 | 2 | 11000 | 17600 | 3 | 6600 | 2200 | 0 | 0 | x1 | 0
Create Required Subscriptions | B | A | 1 | 0.5 | 2000 | 3000 | 0.5 | 1000 | 2000 | 0 | 5 | x2 | 0
Create Cloud Access Hierarchy | C | A | 2 | 1 | 4000 | 6000 | 1 | 2000 | 2000 | 0 | 6 | x3 | 0
Configure Cloud Security Center | D | B | 2 | 1 | 4000 | 6000 | 1 | 2000 | 2000 | 0 | 8 | x4 | 0
Deploy Cloud Networking Core | E | C | 3 | 2 | 6600 | 8800 | 1 | 2200 | 2200 | 0 | 10 | x5 | 0
Validate Networking | F | D | 1 | 0.8 | 2200 | 2640 | 0.2 | 440 | 2200 | 0 | 13 | x6 | 0
Configure VPN Connectivity | G | C | 3 | 1.5 | 6000 | 9000 | 1.5 | 3000 | 2000 | 0 | 14 | x7 | 0
Implement Production Security Blueprint | H | E | 3 | 2 | 6600 | 8800 | 1 | 2200 | 2200 | 0 | 17 | x8 | 0
Enable Network Watching & Capture | I | E | 2 | 1 | 4000 | 6000 | 1 | 2000 | 2000 | 0 | 20 | x9 | 0
Configure Firewalls | J | G | 5 | 2 | 11000 | 17600 | 3 | 6600 | 2200 | 0 | 22 | x10 | 0
Configure Network Peering | K | G | 1 | 0.5 | 2200 | 3300 | 0.5 | 1100 | 2200 | 0 | 27 | x11 | 0
Update IaC Templates | L | G | 3 | 1 | 6000 | 10000 | 2 | 4000 | 2000 | 0 | 28 | x12 | 0
Client Walkthrough | M | F,H,I,J,K,L | 2 | 1 | 4400 | 6600 | 1 | 2200 | 2200 | 0 | 31 | x13 | 0
| DUMMY |  | 33 | 16.3 | 70000 | 105340 | 16.7 | 35340 | 27400 | 0 | 0 |  | 0
Role | Hourly Rate | [5 empty] | Activities | Starting Event | Ending Event
Senior Consultant | 275
Consultant | 250 |  |  |  |  | Develop Infrastructure as Code Templates | A | 0 | 1
[6 empty] | Create Required Subscriptions | B | 1 | 2
[6 empty] | Create Cloud Access Hierarchy | C | 1 | 3
[6 empty] | Configure Cloud Security Center | D | 2 | 4
[6 empty] | Deploy Cloud Networking Core | E | 3 | 5
[6 empty] | Validate Networking | F | 4 | 7
[6 empty] | Configure VPN Connectivity | G | 3 | 6
[6 empty] | Implement Production Security Blueprint | H | 5 | 7
[6 empty] | Enable Network Watching & Capture | I | 5 | 8
[6 empty] | Configure Firewalls | J | 6 | 8
[6 empty] | Configure Network Peering | K | 6 | 9
[6 empty] | Update IaC Templates | L | 6 | 10
[6 empty] | Client Walkthrough | M | 7,8,9,10 | 11
DUMMY

## Sheet2
Name | Activities | Time | Earliest Start | Earliest Finish | Latest Start | Latest Finish | Slack | Critical Path?
Develop Infrastructure as Code Templates | A | 5 | 0 | 5 | 0 | 5 | 0 | Yes
Create Required Subscriptions | B | 1 | 5 | 6 | 5 | 6 | 0 | Yes
Create Cloud Access Hierarchy | C | 2 | 5 | 7 | 6 | 8 | 1 | No
Configure Cloud Security Center | D | 2 | 6 | 8 | 6 | 8 | 0 | Yes
Deploy Cloud Networking Core | E | 3 | 7 | 10 | 8 | 11 | 1 | No
Validate Networking | F | 1 | 8 | 9 | 8 | 9 | 0 | Yes
Configure VPN Connectivity | G | 3 | 7 | 10 | 8 | 11 | 1 | No
Implement Production Security Blueprint | H | 3 | 10 | 13 | 11 | 14 | 1 | No
Enable Network Watching & Capture | I | 2 | 10 | 12 | 11 | 13 | 1 | No
Configure Firewalls | J | 5 | 10 | 15 | 11 | 16 | 1 | No
Configure Network Peering | K | 1 | 10 | 11 | 11 | 12 | 1 | No
Update IaC Templates | L | 3 | 10 | 13 | 11 | 14 | 1 | No
Client Walkthrough | M | 2 | 73 | 75 | 78 | 80 | 5 | No
| DUMMY | 0 | 12 | 12 | 12 | 12 | 0 | Yes